## Read Me
Project Cost Estimating (PCE) Tool | Author: | GHD, Inc.
Utility Management Cycle Step 2 - Identify Needs - Cost Estimating | Owner: | North Coast Resource Partnership
Small Community Toolbox | Version: | 2020-05-04
Introduction
The Project Cost Estimating (PCE) Tool is a workbook that allows the user to input major equipment and construction items to produce a Class 5 cost estimate for the total project. The Association for the Advancement of Cost Engineering International (AACEI) describes a Class 5 cost estimate as
... generally prepared based on very limited information, and subsequently have
wide accuracy ranges. As such, some companies and organizations have elected to
determine that due to the inherent inaccuracies, such estimates cannot be classified
in a conventional and systematic manner. Class 5 estimates, due to the requirements
of end use, may be prepared within a very limited amount of time and with little effort
expended—sometimes requiring less than an hour to prepare. Often, little more than
proposed plant type, location, and capacity are known at the time of estimate
preparation.
...
Typical accuracy ranges for Class 5 estimates are -20% to -50% on the low side, and
+30% to +100% on the high side, depending on the technological complexity of the project,
appropriate reference information and other risks (after inclusion of an appropriate contingency
determination). Ranges could exceed those shown if there are unusual risks (AACEI, 2011).
Methodology
This spreadsheet uses parametric modeling to estimate total project costs from cost estimates for major equipment and construction tasks. Estimated project costs include:
Construction Costs - This tool was designed to be used in conjunction with manufacturer equipment quotes for system improvements. Note in addition to the costs quoted by the equipment supplier there may be additional costs for tax, shipping, installation, appurtenances, contractor mark up and profit. It is recommended that a minimum of 150% of the manufacturer quote be used and up to 300% for more complicated projects.
Other Construction Items Costs self calculate based on user defined percentages. Higher percentages should be used in categories where a project is more complex. For example a higher site work percentage would be used for projects that may require geotechnical analysis and are located on unstable areas. Or, a project upgrading a SCADA system may include higher electrical and instrumentation costs. A project located in a remote site may have higher mobilization and demobilization cost percentage.
Administration - Any administrative costs that are associated with the completion of a project such as budget management, periodic reporting to funding agencies, reimbursement requests, filing permits, managing contractors. This task can be accomplished by the local agency, and or with the support of a consultant. This task can take on average between 4 to 12 hours per month depending on staff experience and project complexity.
Monitoring Plan - As described in the NCRP Application materials, a monitoring plan including goals and measurable objectives is required. This an take between 20 to 60 hours to draft and finalize depending on staff experience.
Labor compliance- Depending on the funding source, a formal labor compliance plan may be needed or other wage monitoring. Based on the funding requirements, a budget of 0.5% to 1% of construction costs is recommended.
Reporting - Develop monthly reports describing work completed, challenges, and strategies for reaching remaining project objectives, and develop the Final Report. This task can take on average between 4 to 8 hours per quarter depending on project complexity. The final report, can take up to 40 hours, but should mostly be comprised of documents developed during the project execution.
Land/Right-of-Way Acquisition - Users should enter the estimated costs for purchasing land or rights of way when the project owner does not have legal rights to the site. These costs are highly depending on the size and use of the property and an appraiser should be contacted to help with an estimate. If the owner has legal rights to construct the project at the site this cost would be zero.
Engineering - This includes consulting fees as well as Professional Engineering designs.
CEQA - The costs for compliance under the California Environmental Quality Act (CEQA) vary based on the type of document. This tool includes a drop down menu for three levels of CEQA documentation: Categorical Exemption, an Initial Study/Mitigated Negative Declaration (MND), and Environmental Impact Report (EIR). The drop down menu links to another sheet in this spreadsheet with further information on the cost model.
NEPA - If the project includes federal funding, compliance under the National Environmental Quality Act (NEPA) is required. Similar to CEQA there is more than one leel of compliance, adn greater costs sould be allocted to more complex projects.
General Permitting- Projects may require multiple types of permits from local, state, and federal agencies. Typical permit preparation costs can range from $1,000 to over $10,000 for more complex envronmental permits. In addition to permit preparation, special environmental studies may be needed to support permitting.
Construction Administration - Construction Administration or Management is necessary to ensure that a project is built in accordance to the designs. Construction Management costs are relative to the complexity of the implementation project. Typical percentage range from 10% to 20%. Higher percentages would be used for more complex project or ones that are located in more rural areas.
Project Close Out - This task is to inspect project components and establish that work is complete. Verify that all project components have been installed and are functioning as specified. Conduct project completion photo monitoring. Prepare record drawings. More complex projects will require more effort, to closeout all the project documentation.
Performance Monitoring - This line item is to cover costs associated with mplementation of the project performance monitoring plan during the grant term.
Contingency - Projects often grow or have unexpected costs which arise. Therefore, it is wise to prepare for this by setting aside funding to deal with these unexpected costs. Teh less certain or detailed the costs typically the higher the contingency should be set.
The user should enter available data into sheet "(1) PCE Tool". The data entered will automatically populate the worksheet titled "(2) NCRP TSB" and "(3) Total Project Cost Chart". The NCRP TSB worksheet populates the North Coast Resource Partnership's Task, Schedule, and Budget (TSB) table.
With the PCE Tool worksheet, all blue filled cells are intended as inputs; though the entire sheet is editable if need be. Add rows as necessary to the Major Equipment and Construction Items section to include all your materials and heavy machinery needs. The cell containing the value for Subtitle 1 may need to be adjusted so all the totals of the above items are included in it. Be conscious of the fact that altering cells of spreadsheets may cause unintended cells to change as well; therefore it is important to check all cells before relying on the data. We have provided typical percentage values for many of the project components for your assistance. However, these are not set values and the cells allow you to change them to whatever you prefer.
Once completed the PCE Tool provides the budgetary data for the NCRP TSB table. The user will then need to add additional detail to the TSB sheet to complete the Task Descriptions, Major Deliverables, Start Date, and End Date columns.
The spreadsheet is provided for the convenience and education of the user. The content and formulas of the spreadsheets can be changed and GHD is not responsible for the accuracy and use of these spreadsheets. The user should verify the completeness and accuracy of the results.
References
AACE International. (2011) Cost Estimate Classification System - As Applied in Engineering, Procurement, and Construction for the Process Industries. Document 18R-97. https://web.aacei.org/

## (1) PCE Tool
(Project Name)
Project Cost Estimating Tool | Major Equipment and Construction Items | [6 empty] | Aligned to NCRP TSB Item
| Unit Items | Quantity | Unit | Unit Cost | Total | Typical Ranges | Notes
| This section is for major |  |  | 0 | 0 | Includes costs for purchase, tax, shipping, and installation. In place cost is typically 150-300% of purchase price.
| equipment and construction |  |  | 0 | 0
| items. It will vary depending on |  |  | 0 | 0
| your type of project. |  |  | 0 | 0
|  |  |  | 0 | 0
| Subtotal 1 |  |  |  | 0 |  |  | D3
| Other Construction Items |  | Cost Estimate |  | Total | Typical Ranges | Notes
| Site Work | 10% |  | of subtotal 1 | 0 | 5-15% of subtotal 1 |  | D2
| Mobilization/ Demolition | 10% |  | of subtotal 1 | 0 | 5-20% of subtotal 1 |  | D2
| Electrical | 15% |  | of subtotal 1 | 0 | 5-125% of subtotal 1 |  | D4
| Instrumentation | 10% |  | of subtotal 1 | 0 | 3-15% of subtotal 1 |  | D5
| Other | 0% |  | of subtotal 1 | 0 | Variable |  | D6
| Project Signage |  |  | of subtotal 1 | 1500 | Varies - Typically $1,000 to $2,000 |  | D7
| Subtotal 2 | 45% |  | of subtotal 1 | 1500
| Non Construction Implementation Costs (Soft Costs) | [7 empty] | 1
| Administration | 2% |  | of (subtotal 1 + 2) | 30 | 1-5% of (subtotal 1 + 2) | Invoicing and auditing. | A1 | 0.02
| Monitoring Plan |  |  | of (subtotal 1 + 2) | 2000 | Varies - Typically $1,500 to $5,000 |  | A2
| Labor Compliance | 1% |  | of (subtotal 1 + 2) | 15 | 0.5-1% of (subtotal 1 + 2) |  | A3
| Reporting | 2% |  | of (subtotal 1 + 2) | 30 | 1-5% of (subtotal 1 + 2) |  | A4 | 0.15
| Land/ROW Acquisition |  |  | of (subtotal 1 + 2) | 0 | Variable |  | B1 | 0.1
| Engineering | 15% |  | of (subtotal 1 + 2) | 225 | 10-20% of (subtotal 1 + 2) | Includes the development of plans and specifications. | C1
| CEQA - Exempt | 5% |  | of (subtotal 1 + 2) | 75 | 1-10% of (subtotal 1 + 2) | Choose One CEQA Option. Incudes costs for developing permit and permit fees. | C2 | 0.02
| NEPA | 0% |  | of (subtotal 1 + 2) | 0 | 5-10% of (subtotal 1 + 2) if required | Only needed when the project uses federal funding. Incudes costs for developing permit and permit fees. | C3
| General Permitting | 2% |  | of (subtotal 1 + 2) | 30 | 5-20% of (subtotal 1 + 2) | Incudes costs for developing permit and permit fees. | C4
| Construction Administration | 10% |  | of (subtotal 1 + 2) | 150 | 7-20% of (subtotal 1 + 2) | Construction/Implementation contracting. | D1
| Project Close Out | 5% |  | of (subtotal 1 + 2) | 75 | 3-8% of (subtotal 1 + 2) | Includes inspection and demobilization. | D8 | 0
| Performance Monitoring | 1% |  | of (subtotal 1 + 2) | 15 | 1-5% of (subtotal 1 + 2) |  | D9
| Contingency | 20% |  | of (subtotal 1 + 2) | 300 | 10-50% of (subtotal 1 + 2) |  | D11 | 0.2
| Subtotal 3 | 63% |  | of (subtotal 1 + 2) | 2945
Cost Summary
| Total Construction Estimate (w/o Contingency) | 100% |  | of (subtotal 1 + 2) | 1500
| Total Estimated Project Costs | 100% |  | of (subtotal 1 + 2 + 3) | 4445
| For Initial Funding Application | 150% |  | of Total Estimated Project Costs | 6667.5

## (2) NCRP TSB
Major Tasks, Schedule and Budget for North Coast Resource Partnership GENERIC IRWM Project Solicitation
Cells in RED indicate either added categories or linked values from the "Project Cost Estimating Tool" worksheet.
Project Name:
Organization Name:
Task # | Major Tasks | Task Description | Major Deliverables | Current Stage of Completion (%) | IRWM Task Budget | Non-State Match | Total Task Budget | Start Date | Completion Date
A | Category (a): Direct Project Administration
1 | Administration | In cooperation with the County of Humboldt sign a sub-grantee agreement for work to be completed on this project. Develop invoices with support documentation. Provide audited financial statements and other deliverables as required | Invoices, audited financial statements and other deliverables as required | 0% | 0 | 0 | 30
2 | Monitoring Plan | Develop Monitoring Plan to include goals and measurable objectives | Final Monitoring Plan | 0% | 0 | 0 | 2000
3 | Labor Compliance Program | Execute service agreement with Labor Compliance Program company | Submission of Labor Compliance Program | 0% | 0 | 0 | 15
4 | Reporting | Develop monthly reports describing work completed, challenges, and strategies for reaching remaining project objectives. Develop Final Report | Quarterly and Final Reports | 0% | 0 | 0 | 30
B | Category (b): Land Purchase/Easement
1 |  |  |  | 0% | 0 | 0 | 0
C | Category (c): Planning/Design/Engineering/Environmental Documentation
1 | Final Design /Plans |  |  | 0% | 0 | 0 | 225
2 | Environmental Documentation: CEQA * |  |  | 0% | 0 | 0 | 75
3 | Environmental Documenation: NEPA |  |  | 0% | 0 | 0 | 0
4 | General Permitting | [5 empty] | 30
5 | Permit Development *: [PLEASE COMPLETE] |  |  | 0% | 0 | 0 | 0
6 |  |  |  | 0% | 0 | 0 | 0
7 |  |  |  | 0% | 0 | 0 | 0
8 |  |  |  | 0% | 0 | 0 | 0
D | Category (d): Construction/Implementation
1 | Construction/Implementation Contracting |  |  | 0% | 0 | 0 | 150
2 | Mobilization and Site Preparation |  |  | 0% | 0 | 0 | 0
3 | Project Construction/Implementation: Major Equipment and Construction Items |  |  | 0% | 0 | 0 | 0
4 | Project Construction/Implementation: Electrical |  |  | 0% | 0 | 0 | 0
5 | Project Construction/Implementation: Instrumentation |  |  | 0% | 0 | 0 | 0
6 | Project Construction/Implementation: Other |  |  | 0% | 0 | 0 | 0
7 | Project Signage | The performance of the project will be monitored in accordance to the Monitoring Plan using the following measurement tools and methods: [PLEASE COMPLETE] |  | 0% | 0 | 0 | 1500
8 | Project Close Out, Inspection & Demobilization | Inspect project components and establish that work is complete. Verify that all project components have been installed and are functioning as specified will be conducted as part of construction inspection and project closeout. Conduct project completion photo monitoring. Prepare record drawings. | As-Built and Record Drawings; Project completion site photos | 0% | 0 | 0 | 75
9 | Project Performance Monitoring | The performance of the project will be monitored in accordance to the Monitoring Plan using the following measurement tools and methods: [PLEASE COMPLETE] |  | 0% | 0 | 0 | 15
10 | Construction Administration | Complete tasks necessary to administer construction contract. Keep daily records of construction activities, inspection, and progress. Conduct project construction photo-monitoring. | Construction Management Logs; Completed construction administration tasks documented in monthly progress reports | 0% | 0 | 0 | 0
11 | Construction Contigency | Additional costs associated with uncertainty in the construction project. |  | 0% | 0 | 0 | #REF!
| Total North Coast Resource Partnership IRWM Grant Request |  |  |  | 0 | 0 | #REF!
| Is Requested Budget scalable by 25%? If yes, indicate scaled totals; if no delete budget amount provided. |  |  |  | 0 | 0 | #REF!
| Is Requested Budget scalable by 50%? If yes, indicate scaled totals; if no delete budget amount provided. |  |  |  | 0 | 0 | #REF!
* CEQA and permitting costs for projects are not an eligible cost for grant reimbursement, unless a project is providing a water-related benefit entirely to DACs, EDAs, or Tribes, or projects implemented by Tribes.

## CEQA
California Environmental Quality Act (CEQA) Level |  |  | Typical Ranges
Subtotal 1 + 2 | 1500
CEQA - Exempt | 5% | 1-10% of (subtotal 1 + 2) | $500 to $5,000
CEQA - MND | 12% | 5-15% of (subtotal 1 + 2) | $30,000 to $50,000
CEQA - EIR | 20% | 10-20% of (subtotal 1 + 2) | over $100,000
This sheet is used to estimate CEQA as a function of project complexity. CEQA consists of multiple components and complexities within those components. At a basic level CEQA can be considered as either one of three categories
Categorically Exempt (Exempt)
Initial Study/ Mitigated Negative Declaration (MND)
Environmental Impact Report (EIR)
There are fixed and variable costs in satisifying the requirements of each CEQA category. Variable costs depend on the number of locations and discoveries involved.
The cost model here is basic assuming a construction and implementation cost proportional model.